## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2025-04-06
Team Number |  | 15
Participant 1 |  | Marko Paradzik
Participant 2 |  | Chamberg Zelimchanov
Participant 3 |  | Ivan Blazevic
Mentor |  | Bernhard Löwenstein
List the IDs of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | https://github.com/tolstoiOM/webshop/issues/28 | 8 | 8 | 0 | 5 | 2
2 | https://github.com/tolstoiOM/webshop/issues/7 | 8 | 8 | 0 | 4 | 2
3 | https://github.com/tolstoiOM/webshop/issues/22 | 4 |  | -4 | 0 | 1
4 | https://github.com/tolstoiOM/webshop/issues/16 | 8 | 16 | 8 | 4 | 2
4 |  |  |  | 4 | 4 | 4