## Tabelle1
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 2025-04-20
Team Number |  | 15
Participant 1 |  | Marko Paradzik
Participant 2 |  | Chamberg Zelimchanov
Participant 3 |  | Ivan Blazevic
Mentor |  | Bernhard Löwenstein
List the IDs of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | https://github.com/tolstoiOM/webshop/issues/28 | 8 | 8 | 0 | 2 | 0
2 | https://github.com/tolstoiOM/webshop/issues/7 | 5 | 5 | 0 | 2 | 0
3 | https://github.com/tolstoiOM/webshop/issues/22 | 4 | 4 | 0 | 1 | 0
4 | https://github.com/tolstoiOM/webshop/issues/16 | 8 | 8 | 0 | 2 | 0
4 | https://github.com/tolstoiOM/webshop/issues/35 | 16 | 16 | 0 | 2 | 0
4 | https://github.com/tolstoiOM/webshop/issues/29 | 16 | 16 | 0 | 4 | 0
4 | https://github.com/tolstoiOM/webshop/issues/53 | 32 | 32 | 0 | 3 | 0
4 | https://github.com/tolstoiOM/webshop/issues/49 | 24 | 24 | 0 | 3 | 0
8 |  |  |  | 0 | 8 | 8